## Proposed KT
Line items to be covered during Due Diligence & KT phase | [7 empty] | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6
Main Task | Sub Task | Participants from Persistent | Participants from Customer | Dependency on Customer ( Y/N) | Proposed meeting slot | Deliverables | Status | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | Comments
Introduction and getting started | Persistent & Customer Team Introduction | Core Team | Customer stakeholders | Yes |  |  | Not Started
| Customer Business overview | Core Team | Business/Product team | Yes |  |  | Not Started | [31 empty] | Legend
| Define and agree Due Diligence daily plan | Core Team | Business/Product team | Yes |  |  | Not Started | [32 empty] | Not Started
Product lines/ Platforms functional Overview | Products Lists and high level details | Core Team | Business/Product team | Yes |  |  | Not Started | [32 empty] | Completed
| Product/Products demo | Core Team | Business/Product team | Yes |  |  | Not Started | [32 empty] | In Progress
| products features details with existing documentation and repository details | Core Team | Business/Product team | Yes |  |  | Not Started | [32 empty] | No session
Application Technical Overview | Architecture | Core Team | Technical team | Yes |  |  | Not Started
| HLD and LLDs | Core Team | Technical team | Yes |  |  | Not Started
| Infrastructure (On prem/Cloud servers, web hosting & DB details) | Core Team | Technical team | Yes |  |  | Not Started
| Deployment & release Strategy, CI/CD pipeline | Core Team | Tech/Deployment team | Yes |  |  | Not Started
| Development & deployment tools | Core Team | Technical team | Yes |  |  | Not Started
| Testing tools/processes | Core Team | Technical team | Yes |  |  | Not Started
Application NFRs | Load/Stress/Concurrent users requirements | Core Team | Technical team | Yes |  |  | Not Started
| Application caching | Core Team | Technical team | Yes |  |  | Not Started
| Security aspects and related processes | Core Team | Technical team | Yes |  |  | Not Started
| Key NFRs to address Scalability, performance, high availability etc. | Core Team | Technical team | Yes |  |  | Not Started
Delivery process details | Project execution methodology like Scrum, Kanban etc. | Core Team | Technical team | Yes |  |  | Not Started
| QA processes for defects end to end cycles | Core Team | Technical team | Yes |  |  | Not Started
| Requirement gathering and documentation details | Core Team | Technical team | Yes |  |  | Not Started
Integration | Third Party Integrations details ( if any ) | Core Team | Technical team | Yes |  |  | Not Started
| Payment providers Integration details(if any) | Core Team | Technical team | Yes |  |  | Not Started
Governance | Agree stakeholders, frequency and agendas | Core Team | Business/Product team | Yes |  |  | Not Started
| Agree risk identification & mitigation process | Core Team | Technical team | Yes |  |  | Not Started
| Quality Process | Core Team | Technical team | Yes |  |  | Not Started
| Communication Plan | Core Team | Technical team | Yes |  |  | Not Started
Team Setup | Code setup, Application Setup | Core Team | NA | Need basis |  |  | Not Started
| Access provisioning process finalization | Core Team | NA | No |  |  | Not Started
| Teams site, alias creation | Core Team | NA | No |  |  | Not Started
System Setup | Understanding on licensed software/setup | Core Team | Technical team | Yes |  |  | Not Started
| Required software for offshore team | Core Team | Technical team | Yes |  |  | Not Started
| Finalization and setting up env for the team | Core Team | IT Team | Yes |  |  | Not Started
| Code Repository access | Core Team | IT Team | Yes |  |  | Not Started
| Software installations | Core Team | Technical team | No |  |  | Not Started
Team Onboarding | Staffing - Profile screening, selections | Core Team | NA | No |  |  | Not Started
| Setup Team onboarding Process | Core Team | NA | No |  |  | Not Started
| Offshore members' Customer email Ids/Accounts/Credentials for Persistent/Customer communications | Core Team | NA | Yes |  |  | Not Started